## To-Do List
TO-DO LIST TEMPLATE
TASK | STATUS | STATUS | DUE DATE | ASSIGNED TO | DELIVERABLE | STATUS KEY | PRIORITY KEY
Find out how to use youtrack | Not Started | High | 2021-08-13 | Barbara |  | Not Started | High
Review user stories | In Progress | High | 2021-08-11 | All |  | In Progress | Medium
Create Acceptance criteria | Not Started | High | 2021-08-11 | All |  | Complete | Low
Create tasks | Not Started | High | 2021-08-11 | All |  | On Hold
Add story points | Not Started | High | 2021-08-11 | All |  | Overdue
PRIORITY | Not Started | High | 2021-08-11 | All
SPRINT | Not Started | High | 2021-08-11 | All
Add team member responsible | Not Started | High | 2021-08-11 | All
Backlog | Not Started | High | 2021-08-11 | All
Task 10
Task 11
Task 12
Task 13
Task 14
Task 15
Task 16
Task 17
Task 18
Task 19
Task 20
Task 21
Task 22
Task 23
Task 24
Task 25
CLICK HERE TO CREATE IN SMARTSHEET

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.