## Sheet1
# | USER | ACTION | EXPECTED OUTCOMES | ACCEPTANCE CRITERIA | Tasks | STORY POINTS (INITIAL ESTIMATES ONLY, TO BE REVIEWED AND PLANNED IN DETAIL | PRIORITY | SPRINT (INITIAL ESTIMATES ONLY, TO BE REVIEWED) | TEAM MEMBER | NOTES
1 | As a trainer, | I want to be able to contact the dog owners nearby | so that I can arrange training sessions
2 | As a trainer, | I need to have access to owner and dog profile informations | so that I can do a personalised trainning | 1. All trainer should have acess to all information related to dogs and trainer, including training history
3 | As a trainer, | I want to send message to other trainers | so that I can arrange events | 1. All trainer should have a way to send messages to other trainers
4 | As a trainer, | I want to be able to create events | so that I can network with other thainers
5 | As a trainer, | I want to be able to create training sessions | so I can organize the trainings schedules
6 | As a trainer, | I want to have a calendar | so that I can visualize all ativities scheduled during the month
7 | As a trainer, | I want to know the estimated driving time to the parks nearby | so that I can choose which one is more suitable to me
8 | As a trainer, | I need to have access trainers profile informations
9 | As a trainer, | I want to be able to delete a training session
10 | As a trainer, | I want to be able to modify a training session
11 | As a dog owner, | I want to be able to view other dog's owner information | so that I can choose the right dog to play with
12 | As a dog owner, | I want to able to view the trainer's profile information | select the best suitable trainer
13 | As a dog owner, | I want to be send message to all users | communicate with others
14 | As a dog owner, | I want to be able to leave activities that I join
15 | As a dog owner, | I want to be able to create/schedule an activities
16 | As a dog owner, | I want to be able to check any activities nearby | so that I can participate in the activities | 1. All users should be able to view available activies based on the date they put on calender 2. All activities will show the distance of it from the dog owner |  |  | High | One |  | List activities
17 | As a dog owner, | I want to be able to book a training session | so that I can train my dog | 1. All users should be able to check available training session 2. Training sessions should include training date, training time, details and trainer's name |  |  | High | One |  | List training
18 | As a dog owner, | I want ot be able to add and update my details | so that all displayed information is correct | 1. All users should be able to add their details 2. All users should be able to update their details |  |  | High | One |  | Update details
19 | As a dog owner, | I want to be able to create groups | so that I can schedule activities with my group directly
20 | As a dog owner, | I want to be able to set reminders for the events and training sessions | so that I can remeber before the event happen
21 | As a dog owner, | I want to be able to invite friends to events
22 | As a dog owner, | I want to have a calendar | so that I can visualize all ativities scheduled during the month
23 | As a dog owner, | I want to know the estimated driving time to the parks nearby | so that I can choose which one is more suitable to me
24 | As a dog owner, | I want to have a visual image of a map | so that I can visualize all parks and users nearby | 1. All users should be able to view a map with available users and park nearby |  |  | High | Two |  | Map visualisation
25 | As a dog owner , | I want to be able t o cancel an training session tha I have booked | so that I don't incovinence anyone in case of unforeseen circumstances | 1. All users should be able to delete a training session that he/she has booked 2. The user must have book the activity before be able to cancel it
26 | As a dog owner , | I want to be able to delete a group | so that I can change my group preference | 1. User should be able to view all the groups that he/she had joined 2. User is able to delete the group
27
28 | As a dog owner , | I want to be able to change activities
29 | As a dog owner , | I want to be able to delete a person from the group
30 | As a dog owner , | I want to be able to cancel an activity that I created

## Story points estimation cheat s
https://teamhood.com/agile/story-point-estimation-table/